## Checklist
Checklist Hyperlinks
EXHIBIT A - DESIGN SCOPE CHECKLIST - ADDENDUM #2 dated 9/10/2020 |  |  | Design Services
Design Responsibility
Construction Procurement Services
Construction Administration
Project Name: | Racine County Secure Residential Care Center for Children and Youth (SRCCCY) |  | Sustainability Services
Location: | Racine, WI |  | Virtual Design and Construction
CHANGES PER ADDENDUM SHOWN IN RED FONT |  |  | Contract Agreements
Included? (Y/N) | DESIGN SERVICES
Preliminary Design Consultant to prepare a preliminary design, including a report identifying any deviations from the Owner's criteria.
Program Validation
Schematic Design
Design Development
Construction Documents Consultant shall further develop the design in accordance with discussions and plans developed during the preliminary design stages and prepare construction documents for the consultant's portion of the project. The Construction Document stage will be divided into three design package releases as detailed in the Schedule included in Exhibit C.
Multi-Discipline Coordination Coordinate services provided by the Owner, the Owner's consultants, the Construction Manager as they relate to this consultants portion of the project.
Project Design Presentations Make presentations to explain the design of the Project to the Owner, Construction Manager, governmental authorities, or others
Governmental Authorities Submissions File documents for approval of governmental authorities having jurisdiction over the Project
Trips/Meetings Quantity of requested meetings detailed by design and project phase in Section 3 of the RFP document.
Drawings and Specifications Copies Provide electronic copies of all drawings and specifications.
Included? (Y/N) | DESIGN RESPONSIBILITY
CONSULTANT
Architect of Record
Associate Architect
Interior Designer
Structural
No | Geotechnical
Civil
Landscaping
Mechanical
Electrical
Plumbing
Fire Protection
No | Surveying
No | Utility Locating
No | Environmental
LEED / Sustainability
Low Voltage / Tel Com
Security
Audio Visual
No | Commissioning
No | Lab Planner
Elevator Consultant
Food Service Consultant
ADA Consultant
Code Consultant
No | Process Design
Specialty / Other
No | Construction Material & Testing
Signage / Graphics
Furniture, Fixtures & Equipment
Included? (Y/N) | CONSTRUCTION PROCUREMENT SERVICES
Yes | Substitutions Review requests for substitutions, if permitted by the bidding/proposal documents
Yes | Bid/Proposal Conference Participate in a pre-bid conference for prospective bidders
Yes | Addenda Prepare responses to questions from prospective bidders/proposers and provide clarifications and interpretations in the form of addenda
Yes | Community Outreach Participate in outreach to include community, trade, or workforce development program support
Included? (Y/N) | CONSTRUCTION ADMINISTRATION
Yes | Contract Administration Utilize Gilbane systems for documentation (i.e. submittals, RFI's, field reports, billings), see Exhibit J Technology Requirements.
Yes | Meetings Attend meetings as detailed in Section 3 of the RFP document.
Yes | Requests for Information Review requests by the Construction Manager/Contractors for additional information about the Contract Documents.
Yes | Submittals Review and approve submittals for the purpose of checking for conformance with information given and the design concept expressed in the Contract Documents.
Yes | Site Evaluations Visit the site weekly for observation of the Work and keep the Construction Manager informed about the quality of the Work. Report any known deviations from the contract documents or defects and deficiencies observed in the Work.
Yes | Cost Evaluations Provide review and approval of contractor change orders as necessary and review/certification of contractor monthly payment requisitions.
Yes | Project Completion Conduct inspections of the Work to assist the Construction Manager in determining the date of Substantial Completion. Provide complete electronic record drawings to the Owner as detailed in Section 3 of the RFP document at completion of the project.
Yes | Commissioning Participate in commissioning process as detailed in Section 3 of the RFP document.
Yes | Punchlist Participate in on-site generation and signoff of punchlist items, to be issued in form compatible with Gilbane's QC software.
Yes | Project Eleven Month Review Provide an eleven (11) month warranty walk-through with Owner and Construction Manager.
Included? (Y/N) | VIRTUAL DESIGN AND CONSTRUCTION
Yes | Project will be drawn in latest version of Revit version 2020 from inception except for the following disciplines:
Yes | Maintain record documents within the model to capture design changes and RFIs issued during the CA phase
Yes | Incorporate as-built information from contractors into the model during the CA phase
Included? (Y/N) | CONTRACT AGREEMENTS
Professional Liability: As listed in Sample AIA Agreement Exhibit G.
Have you read and accept Racine County's standard contract?
Have you read and accept Gilbane's design deliverables matrix?
Have you read and accept the overall project schedule?

## Cost of Work
EXHIBIT A - DESIGN SCOPE CHECKLIST - ADDENDUM #2 dated 9/10/2020
Project Name: | Racine County Secure Residential Care Center for Children and Youth (SRCCCY)
Location: | Racine, WI
CHANGES PER ADDENDUM INDICATED WITH RED BAR IN LEFT MARGIN
COST OF WORK
DESIGN SERVICES
Program/Pre-Design Phase | 0
Schematic Phase | 0
Design Development Phase | 0
Construction Document Phase | 0
PROCUREMENT SERVICES
Bidding/Permit Prep | 0
CONTRACT ADMINISTRATION
Construction Administration Phase | 0
Reimbursable Expenses | 0
INSURANCE
Professional Liability Insurance | 0
SUMMARY
TOTAL | 0
DESIGN RESPONSIBILITY
Architect of Record | 0
Associate Architect | 0
Interior Designer | 0
Structural | 0
Civil | 0
Landscaping | 0
Mechanical | 0
Electrical | 0
Plumbing | 0
Fire Protection | 0
LEED / Sustainability | 0
Low Voltage / Tel Com | 0
Security | 0
Audio Visual | 0
Lab Planner | 0
Elevator Consultant | 0
Food Service Consultant | 0
ADA Consultant | 0
Code Consultant | 0
Process Design | 0
Specialty / Other | 0
Signage / Graphics | 0
Furniture, Fixtures & Equipment | 0
SUMMARY
TOTAL | 0
Design Alternates
1) Provide ADD alternate for inclusion of design, engineering, and coordination of a pedestrian bridge across Taylor Avenue as indicated in Exhibit D -Site Plan.
ADD | 0
Economic Inclusion and Diverse Business Intent
Participation: | Provide Intent Form Included in Exhibit I - Economic Inclusion Plan
REIMBURSABLES
DESCRIPTION | UNIT | UNIT COST | QUANTITY | TOTAL
Office supplies
Postage, shipping
Cell phones
Document reproduction
Local travel expenses
Travel cost per trip
Non-local travel expenses
Photography
Insurance (Specify Type)
Professional Liability insurance
Other
TOTAL |  |  |  | 0
ADDITIONAL SERVICES
Include billing rate list of team members, including all associated burden and markups
TEAM MEMBER | TITLE | BILLING RATE
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL |  | 0
Lump Sum
Reimbursed at Cost; see itemized estimate below